## Summary
Moonlit Heist: Improvement Tracker
Counts below update from the Status, Phase, Impact and Effort columns on the Improvements sheet.
Overall | Count
Total items | 61
To do | 61
In progress | 0
Done | 0
Skipped | 0
Percent done (excluding skipped) | 0%
By category | Items | Done | % done
Navigation and flow | 11 | 0 | 0%
Gameplay and design | 12 | 0 | 0%
Scoring and balance | 7 | 0 | 0%
Content and story | 7 | 0 | 0%
UI and QoL | 9 | 0 | 0%
Code quality | 7 | 0 | 0%
Bugs and risks | 4 | 0 | 0%
Testing and presentation | 4 | 0 | 0%
Total | 61 | 0 | 0% | OK
By phase | Items | Done | % done
Phase 1 | 6 | 0 | 0%
Phase 2 | 9 | 0 | 0%
Phase 3 | 7 | 0 | 0%
Phase 4 | 10 | 0 | 0%
Backlog | 29 | 0 | 0%
Impact vs effort (item count) | S | M | L
High | 4 | 4 | 1
Med | 14 | 12 | 0
Low | 20 | 4 | 2
Notes
Effort: S = under an hour, M = a few hours, L = a day or more.
Where the original list gave a range (S-M), Effort is set to M.
Phases come from the suggested order: Phase 1 first (small, high impact), then 2, 3 and 4.
Value score (Improvements, column K) = impact weight (High 3, Med 2, Low 1) divided by effort weight (S 1, M 2, L 3). Higher means better return for the work.
Cells to edit: Phase, Status, Owner and Notes (cream background, blue text) on the Improvements sheet.
Item 53 (library rules) is High impact only if the rubric limits libraries; ask the instructor.

## Improvements
ID | Category | Item | Why / where in game.cpp | Impact | Effort | Phase | Status | Owner | Notes | Value score
1 | Navigation and flow | Back navigation in deduction | deduction() is a fixed 4-step chain. Steps 2 to 4 use askChoice(5, false), so there is no 0 option. | High | S | Phase 1 | To do |  |  | 3
2 | Navigation and flow | Confirmation screen before submitting | Show the 4 choices with Confirm / Change an answer. One wrong pick currently ends the game. | High | S | Phase 1 | To do |  |  | 3
3 | Navigation and flow | Dialogue log (L key) | waitKey() moves on and the reply is gone. Store the last N lines in an array like notes. | High | M | Phase 2 | To do |  |  | 1.5
4 | Navigation and flow | C and N hotkeys inside interviews and deduction | Case File and Notes only work in exploreLoop(). The player can't check the evidence log while choosing evidence. | High | M | Phase 1 | To do |  |  | 1.5
5 | Navigation and flow | Page back in Notes | showNotes() only goes forward through its pages. | Med | S | Backlog | To do |  |  | 2
6 | Navigation and flow | Confirm on Q | Q returns to the menu and wipes all progress with no warning. | Med | S | Phase 2 | To do |  |  | 2
7 | Navigation and flow | Arrow keys in the exploration map | They work only in the main menu (readMenuKey). | Med | S | Backlog | To do |  |  | 2
8 | Navigation and flow | Esc as Back | Treat Esc as 0 in askChoice. Careful on Mac/Linux, where arrow keys also start with Esc. | Low | S | Backlog | To do |  |  | 1
9 | Navigation and flow | Quick profile view during an interview | Let the player open the suspect's file with one key. | Low | S | Backlog | To do |  |  | 1
10 | Navigation and flow | Retry deduction after Game Over | playGame() calls resetGame() and wipes everything. Offer retry deduction as an easy mode; keep full restart as default. | Med | M | Backlog | To do |  |  | 1
11 | Navigation and flow | Save and load | Needs <fstream>, which isn't on the allowed library list. | Low | L | Backlog | To do |  |  | 0.33333
12 | Gameplay and design | Present Evidence option | Doc says to question statements to uncover inconsistencies, but interviews only pick the best of 3 questions. Let the player pick evidence to catch a lie. | High | L | Phase 3 | To do |  |  | 1
13 | Gameplay and design | Interaction prompt | Show '[E] Talk to Julian' or '[E] Examine desk' when adjacent. The player currently has to guess. | High | S | Phase 1 | To do |  |  | 3
14 | Gameplay and design | Objective line | Show a line like 'Interview all 5 suspects (2/5)'. | Med | S | Phase 2 | To do |  |  | 2
15 | Gameplay and design | Hint key (H) | The solution is a chain (Arthur, cufflink, desk ink, deduction). A stuck player has no direction, so add a hint that costs points. | Med | M | Backlog | To do |  |  | 1
16 | Gameplay and design | Flag-based unlocks | Unlocks only check evidence (needEvidence). Dev notes say Evelyn's phone topic should unlock after Arthur's testimony, but it is always visible. | Med | M | Phase 3 | To do |  |  | 1
17 | Gameplay and design | Payoff for red herrings | Handbag catalog and garden soil are found but never used in dialogue. Add topics for Evelyn and Gideon that need them. | Med | M | Phase 3 | To do |  |  | 1
18 | Gameplay and design | More searchable objects | Only 4 exist ($ & % ^). The timeline has the teacup, closet-threshold wipe and brass bookend. | Med | M | Phase 3 | To do |  |  | 1
19 | Gameplay and design | Grace (the owner) as an NPC | She is in the doc but not in the game. She could explain the primary key and give the first hint. | Med | M | Phase 3 | To do |  |  | 1
20 | Gameplay and design | Shuffle answer order | tp.correct is fixed, so replays can be memorized. | Med | M | Phase 2 | To do |  |  | 1
21 | Gameplay and design | Suspects react to evidence | For example, Julian says something once you have found the ink. | Low | M | Backlog | To do |  |  | 0.5
22 | Gameplay and design | Moving NPCs | Suspects are static (x, y fixed). | Low | L | Backlog | To do |  |  | 0.33333
23 | Gameplay and design | Difficulty modes | Easy gives hints and retry. Hard has no hints. | Low | M | Backlog | To do |  |  | 0.5
24 | Scoring and balance | Scoring cap mismatch | 16 topics x 50 = 800 raw points but the score is capped at 400, so up to 20 wrong answers cost nothing. Use +25 per answer or rescale. | High | S | Phase 1 | To do |  |  | 3
25 | Scoring and balance | Show the efficiency bonus | It is invisible now. Show 'Bonus: 100 (-10 per mistake)' in the side panel. | Med | S | Phase 2 | To do |  |  | 2
26 | Scoring and balance | Partial credit for the bonus | The bonus is 0 until all 5 suspects are fully done. | Low | S | Backlog | To do |  |  | 1
27 | Scoring and balance | Game Over shows 0 | Doc says the score should reflect performance. Decide whether Game Over shows the investigation score. | Low | S | Backlog | To do |  |  | 1
28 | Scoring and balance | Guessable deduction | Game Over names exactly which parts were wrong and correct positions are fixed ([2] reasoning, [4] motive, [3] evidence). Solvable in about 4 tries. Shuffle options and consider an attempt penalty. | High | M | Phase 2 | To do |  |  | 1.5
29 | Scoring and balance | Reasoning option 2 spoils the answer | The correct reasoning text states the full solution (Julian, spare key, desk). Make options shorter and equal in style. | Med | S | Phase 2 | To do |  |  | 2
30 | Scoring and balance | Deduction allowed from turn one | Consider requiring some progress, or counting attempts. | Low | S | Backlog | To do |  |  | 1
31 | Content and story | Prologue and first-time tutorial hints | The game just drops you at the map. | Med | S | Backlog | To do |  |  | 2
32 | Content and story | Unlock Case File timeline entries | The timeline is static. Unlock entries like 10:15 light and 11:15 cufflink as clues are found. | Med | S | Phase 3 | To do |  |  | 2
33 | Content and story | Undiscovered evidence shown as ??? | So players know what they are missing. | Low | S | Backlog | To do |  |  | 1
34 | Content and story | Organize Notes by suspect, highlight contradictions | Notes are a flat list now. | Med | M | Phase 3 | To do |  |  | 1
35 | Content and story | Epilogue timeline recap | After a win, recap the true heist timeline (10:15 key, 10:40 theft, 11:15 trap). | Low | S | Backlog | To do |  |  | 1
36 | Content and story | Final stats screen | Show wrong answers, evidence found (x/8) and topics done (x/16). | Low | S | Backlog | To do |  |  | 1
37 | Content and story | Update the instructions screen | Mention [0] Back and the dialogue log. | Low | S | Backlog | To do |  |  | 1
38 | UI and QoL | Replace system("cls") | It flickers on every step and spawns a process. Print "\033[H\033[2J" instead. setupConsole() already enables ANSI on Windows. | Med | S | Phase 1 | To do |  |  | 2
39 | UI and QoL | Console size check | Layout needs about 100 columns (map 60 + panel + dialogue width 86). Warn or resize. | Med | S | Backlog | To do |  |  | 2
40 | UI and QoL | Room labels on the map | The player has to read the side panel to know where they are. Also highlight objects when adjacent. | Med | M | Backlog | To do |  |  | 1
41 | UI and QoL | Interview progress display | Show 'Julian 2/4' in the Persons of Interest list and on the map panel. | Med | S | Phase 2 | To do |  |  | 2
42 | UI and QoL | NEW tag on topics | Mark topics unlocked by evidence. A ! over a suspect on the map would help too. | Med | S | Phase 2 | To do |  |  | 2
43 | UI and QoL | Fix the Status panel | Only 3 lines of 31 characters, so longer messages get cut. | Low | S | Backlog | To do |  |  | 1
44 | UI and QoL | ASCII fallback | The symbols ◆ ═ ✔ ✘ ★ need UTF-8. | Low | S | Backlog | To do |  |  | 1
45 | UI and QoL | Optional bell sound | Print \a on correct and wrong answers. | Low | S | Backlog | To do |  |  | 1
46 | UI and QoL | Typewriter text effect | Needs a sleep function, which is outside the allowed libraries. | Low | M | Backlog | To do |  |  | 0.5
47 | Code quality | Split the 1,724-line file | Separate map, UI, dialogue and logic, if the instructor allows it. | Med | M | Phase 4 | To do |  |  | 1
48 | Code quality | Room table for getRoomName() | It hard-codes room boundaries (17, 31, 44) separately from gameMap. Editing the map can silently break the labels. | Med | M | Phase 4 | To do |  |  | 1
49 | Code quality | One helper for centering math | showInstructions, showCredits and drawMenu repeat the same padding code. | Low | S | Phase 4 | To do |  |  | 1
50 | Code quality | Replace magic numbers with constants | For example the start position 30, 10 and the numbers 8 and 12. | Low | S | Phase 4 | To do |  |  | 1
51 | Code quality | Symbol-to-handler table in exploreLoop() | Replace the if chain for $ & % ^. | Low | S | Phase 4 | To do |  |  | 1
52 | Code quality | Group global state into one struct | Suspects, evidence, notes and counters are separate globals. | Low | M | Phase 4 | To do |  |  | 0.5
53 | Code quality | Library rules | <windows.h>, <termios.h> and <unistd.h> aren't on the beginner list. High impact if the rubric is strict, so ask the instructor. | High | M | Phase 4 | To do |  |  | 1.5
54 | Bugs and risks | Multiple adjacent suspects | With two suspects within 1 tile, the lower index wins, and diagonals count. Pick the nearest instead. | Low | S | Backlog | To do |  |  | 1
55 | Bugs and risks | addNote() silently drops notes at MAX_NOTES | MAX_NOTES is 40 and only about 20 are needed now, so it is safe. Add a warning if topics are added. | Low | S | Backlog | To do |  |  | 1
56 | Bugs and risks | Interview-found evidence adds no note | foundEvidence(..., "") passes an empty note for evidence revealed by a topic. | Low | S | Backlog | To do |  |  | 1
57 | Bugs and risks | exit(0) on any read failure | Ends the game with no message. | Low | S | Backlog | To do |  |  | 1
58 | Testing and presentation | Hidden debug key | Reveal all evidence and jump to deduction, for demos and testing. | Med | S | Phase 4 | To do |  |  | 2
59 | Testing and presentation | Playtest checklist | All 15 wrong-answer combinations, every topic right and wrong, each rank, a small console, Mac/Linux. | Med | M | Phase 4 | To do |  |  | 1
60 | Testing and presentation | Golden-path demo script | A scripted run for the presentation. | Med | S | Phase 4 | To do |  |  | 2
61 | Testing and presentation | Update the flowcharts after changes | Regenerate the four .mmd charts when the code changes. | Low | S | Backlog | To do |  |  | 1